## PWA
Project Worthiness Analysis
Criteria | Line activity |  |  | Small Project |  |  | Project |  |  | Selection |  | Selection
Number of divisions involved | 1 area | 1 | 0 | 2 areas | 2 | 2 | ≥ 3 areas | 3 | 0 | 2 areas | 1 area | 2 areas | ≥ 3 areas
Size of the entire project team | < 5 person | 1 | 0 | 6-9 person | 1 | 1 | ≥ 10 person | 1 | 0 | 6-9 person | < 5 person | 6-9 person | ≥ 10 person
Effort | < 50 days | 1 | 0 | 51-99 days | 1 | 1 | ≥ 100 days | 1 | 0 | 51-99 days | < 50 days | 51-99 days | ≥ 100 days
Invest | < 50 TUSD | 1 | 0 | 51-99 TUSD | 2 | 2 | ≥ 100 TUSD | 3 | 0 | 51-99 TUSD | < 50 TUSD | 51-99 TUSD | ≥ 100 TUSD
Duration | < 3 months | 1 | 0 | 4-9 months | 1 | 1 | ≥ 10 months | 1 | 0 | 4-9 months | < 3 months | 4-9 months | ≥ 10 months
Complexity of scope | low | 1 | 0 | medium | 1 | 1 | high | 1 | 0 | medium | low | medium | high
Novelty for people involved | low | 3 | 0 | medium | 3 | 3 | high | 3 | 0 | medium | low | medium | high
Quality risk | low | 1 | 0 | medium | 1 | 1 | high | 1 | 0 | medium | low | medium | high
External impact | low | 1 | 0 | medium | 1 | 1 | high | 1 | 0 | medium | low | medium | high
Total |  |  | 0 |  |  | 13 |  |  | 0
[7 empty] | Recommendation |  |  | Small Project
The sheet is protected, only the cells of the "Selection" column can be modified.
Change the entries in the Selection column, the recommendation will be calculated.
The calculation is made using the points of columns F, I, L, which are transferred to columns G, J, M depending on the selection and summed up in line 14.
The name of the category with the highest score is included in the recommendation in N15.
To unprotect the sheet, enter the password "TPG".
All names and numbers can then be edited directly.